## Sheet1
Description	Assessment	Risk(Likelihood)	Impact	Responsibility	Current Mitigation	Proposed Mitigation	Response
Cloud platform for VM stops functioning	App ceases	Low	High	GCP	Repository		Create a new VM so app can function again
Database hacked	Data altered or deleted	Low	Medium	Kieran A	No sensitive data held	Data uploaded to database backed up	New VM to restore correct data
Jenkins VM stops working	Automated testing will not run	Low	Low	Kieran A	Back up copies of script and other necessities		Create new Jenkins VM so automated testing can resume